## Project Timeline
INTEGRATED CONCENTRATING SOLAR MODELICA MODEL
TIMELINE
PROJECT DETAILS
DATE | MILESTONE | POSITION | BASELINE
2014-06-26 | Modelica Example Models | 10 | 1
2014-07-03 | Started: ICSolar Modelica Model | 20 | 1
2014-07-04 | Started: Context & Weather Data and Heat Receiver | -10 | 1
2014-07-05 | Systems Diagram | 10 | 1
2014-07-07 | Started: Envelope Cassette, Glazing Losses, and Self Shading | -20 | 1
2014-07-10 | Started: Stack, Module, CPV Optical Performance, and Lens Losses | 20 | 1
2014-07-18 | Finished: Module, Heat Receiver, CPV Optical Performance, and Lens Losses | -10 | 1
2014-07-22 | Finished: Packaged Models into one Modelica File | 10 | 1
2014-07-25 | Progress: Simplified Air Cavity Temperature, High Fidelity CFD Model Later | -20 | 1
2014-07-29 | Finished: Weather Data & Context | 20 | 1
2014-08-01 | Finished: Glazing Losses | -10 | 1
2014-08-06 | Goal: Temperature Balance in Cavity between Exterior and Interior | 10 | 1
2014-08-08 | Goal: System Oriented Self Shading | -20 | 1
2014-08-29 | Goal: Working ICSolar Modelica Model | 20 | 1
2014-09-05 | Goal: System of Systems Co-Simulated Model | -10 | 1
2014-10-31 | Goal: Implement High Fidelity CFD ODE into Modelica | 10 | 1
2014-11-07 | Goal: Improved System of Systems Co-Simulated Model | -20 | 1
2014-12-26 | Goal: Create Framework for CASE FMU Library | 20 | 1
1
1
Project Timeline Tips:
The role of the Position values in the Project Details table is to prevent the Milestone labels from overlapping each other on the timeline. Use positive numbers to position labels above the timeline and negative numbers to position them below.
To add additional Milestones, either insert new rows within the table or start typing below the last table entry and the table will automatically expand to accommodate your newly added data.